## Table 1
USER ID | USER STORY | PRIORITY | RISK | STORY POINTS | SPRINT EFFORT | DEPENDANCIES
Sprint 1 |  |  |  |  | 18
5 | As an athlete, I want to enter exercise that I do, so that I can track my activity. | Must Do | High | 8
15 | As an athlete, I want to enter fitness goals, so that I have a goal to obtain | Must Do | Moderate | 2
19 | As an athlete, I want to link a coach to my account, so they can track my progress | Must Do | High | 8
Sprint 2 |  |  |  |  | 18
8 | As an athlete, I want to be able to enter what I eat for each meal, so that I can track my nutrition | Must Do | Moderate | 5
1 | As an athlete, I want to enter weight and height information, so that I can use that information to track and calculate other health information | Must Do | Low | 3
21 | As a coach, I want to see the amount of exericse that my athletes are completing, so that I can see how much they are exercisin | Must Do | Moderate | 5 |  | 5 , 19
22 | As a coach, I want to see what my athletes are eating, so that I can determine if their diet is appropriate for their trainin | Must Do | Moderate | 5 |  | 19, 8
Sprint 3 |  |  |  |  | 20
20 | As a coach, I want to see the height and weight information of my athletes, so that I can adjust their trainings and diets appropriatel | Must Do | Moderate | 5 |  | 1, 19
16 | As an athlete, I want to enter dietary goals, so that I have a goal to obtain | Must Do | Moderate | 2
2 | As an athlete, I want the application to track my weight, so that I can see my improvements. | Must Do | Low | 5 |  | 1
18 | As an athlete, I want the application to notify me if I am not meeting my dietary goals, so that I can stay on track to meeting my goals | Should Do | Moderate | 3 |  | 16
7 | As an athlete, I want the application to notify me if I am not exercising frequently enough, so that I stay in shape | Should Do | Moderate | 3 |  | 5
9 | As an athlete, I want to enter the calories for the food I eat, so that I know how much I am consuming | Should Do | Moderate | 2 |  | 8
Sprint 4 |  |  |  |  | 20
12 | As an athlete, I want to enter the amount of water I consume, so that I can track my hydration. | Should Do | Moderate | 3
17 | As an athlete, I want the application to notify me if I am not meeting my fitness goals, so that I can stay on track to meeting my goals | Should Do | Moderate | 3
24 | As a coach, I want to see the fitness goals of my atheletes, so that I can adjust their trainings to meet their goal | Should Do | Low | 3 |  | 15
25 | As a coach, I want to see the dietary goals of my athletes, so that I can adjust their diet to meet their goal | Should Do | Low | 3 |  | 16
3 | As an athlete, I want to set a target weight, so that I have a weight goal to reach. | Should Do | Low | 1
14 | As an athlete, I want the application to notify me to remind me to drink water, so that I am constantly hydrating | Could Do | Moderate | 3 |  | 12
11 | As an athlete, I want the application to notify me if I am not meeting my suggested calorie intake, so that I am following my diet accurately | Could Do | Moderate | 2 |  | 9
13 | As an athlete, I want the application to calculate a suggested amount of water that I should consume based on my height and weight, so that I am accurately hydrating. | Could Do | High | 2 |  | 9
Backlog |  |  |  |  | 15
6 | As an athlete, I want the application to calculate the amount of calories burned in a workout based on the activity and my body size, so that I know the results of my workout | Could Do | Low | 5
10 | As an athlete, I want the application to calculate a suggested amount of calories for each meal based on my height and weight, so I can adjust my diet accordingly | Could Do | Low | 3
4 | As an athlete, I want the application to calculate how many pounds per week I should lose, so that I can see if I'm on track with my weight goals. | Could Do | Moderate | 2
23 | As a coach, I want to see how much water my athletes are drinking, so that I can make sure they are hydrating appropriately | Could Do | Moderate | 5